## Sheet2
Home Page | Start Date | Deadline
index-new1 | 2017-01-08 | 2017-01-16
- Images Slider
- Right Menu
- Footer + NewsLetter
- SEO URL
- PobUp screen | 2017-01-22 | 2017-01-23
- NEW ARRIVAL | 2017-01-08 | 2017-01-16
- Best-sellers
Infomation Pages
about-us | 2017-01-17 | 2017-01-19
call-For-delivery | 2017-01-17
careers | Testing/23Jan2017 | Testing/23Jan2017
delivery-charges | 2017-01-17 | 2017-01-19
Feedback | Testing/23Jan2017 | Testing/23Jan2017
free-Shipping-inside-Kuwait | 2017-01-17 | 2017-01-19
help
our-privacy-policy
our-services
return-and-exchange
shipping-policy
Main Menu (inner page) | 2017-01-22 | 2017-01-23
Tips-advice | 2017-01-17 | 2017-01-19
Core Bussiness Pages
accessories | 2017-01-27 | 2017-02-02
children
sunglass
contact-lenses
eyewear
best-sellers
frame-search
anesthesia-plano
frames
shopping-cart
special-offers
search | 2017-01-19 | 2017-01-19
sitemap
news | 2017-01-22 | 2017-01-23
news-details | 2017-01-22 | 2017-01-23
Accounts Pages
my-account | 2017-01-24 | 2017-01-25
signin | 2017-01-24 | 2017-01-25
register | 2017-01-24 | 2017-01-25
Responsive
QA | 2017-02-03 | 2017-02-04
Extra Time (pages not designed)
Forget Password | 2017-01-24 | 2017-01-25
account/success (after register new user)
My Account Menu (new)
Address Book
Add new address
Edite Address book
newsletter
wishlist | 2017-02-14 | 2017-02-14
Waleed Optics in Arabic Language
Start Date: | 2017-02-05 | 2017-02-05
End Date: | 2017-02-13 | 2017-02-13
Achievements
Uploade "Waleed Optics" Website Online | 2017-02-14
Get notes from Mr.Omar Aburass |  | 2017-02-14
Call customer on skype with 'Mr.Omar Aburass' |  | 2017-02-15
Get notes from Mr.Omar Aburass, by Customer (1 note)
Current Status | Website Online and waiting customer notes
Rework
Payment Gateway Merchant Integration , Received files via emial in 19/02/2017 | 2017-02-19
The Current Status | try work with payment files
Prpblems: | I am need to working demo and display how to integrate with my website... I am tested it but not working, I am need to explain it. Note: I am try to download files from online there is no any changes with the files sent via email. This is link where try to install payment kent
Created by: Mr.Omar Aburass
Develop by: Ibtisam Al-hitteh, Php Developer