## Sheet1
Balloons & Party Supplies | Duration Details by hours | Duration | start date | End date | actual start | actual end | Percent complete | build
home page |  | 5 days | 2017-03-12 | 2017-03-16 | 2017-03-13 | 2017-03-21 | 100% | build #1-22/03/2017
-Main menu for full screen +mobile menu | 6 hours |  | 2017-03-13 | 2017-03-13 | 13/03/2017 | 2017-03-15 | 100%
-header | 4 hours |  | 2017-03-13 | 2017-03-14 | 2017-03-16 | 2017-03-16 | 100%
-Main Banner | 8 hours |  | 2017-03-14 | 2017-03-15
-Latest Products | 10 hours |  | 2017-03-15 | 2017-03-16 | 19/03/2017 | 19/03/2017 | 100%
-Featured Products | 4 hours |  | 2017-03-16 | 2017-03-16 | 2017-03-20 | 2017-03-20 | 100%
-Description | 2 hours |  | 19/03/2017 | 2017-03-19 | 2017-03-21 | 2017-03-21 | 100%
-Footer | 6 hours |  | 19/03/2017 | 2017-03-19
General
-index page | 6 hours | 2 days | 2017-03-20 | 2017-03-20 | 2017-03-23 | 2017-03-23 | 100% | build #2-28/03/2017
-cart page | 6 hours |  | 2017-03-20 | 2017-03-21 | 23/03/2017 | 2017-03-26 | 100%
-favorites page | 4 hours |  | 2017-03-21 | 2017-03-21 | 2017-03-27 | 2017-03-27 | 100%
-user profile account information page | 8 hours | 4 days | 2017-03-22 | 2017-03-22
-user profile address book page | 8 hours |  | 2017-03-23 | 2017-03-23
-user profile change password page | 4 hours |  | 2017-03-26 | 2017-03-26
-user profile orders page | 8 hours |  | 2017-03-26 | 2017-03-27
-register | 4 hours |  | 2017-03-27 | 2017-03-27
-confetti | 10 hours | 2 days | 2017-03-28 | 2017-03-29
-confetti details | 6 hours |  | 2017-03-29 | 2017-03-29
-Regular Latest Balloons | 32 hours | 3 days | 2017-03-29 | 2017-04-02
-Balloons main inner | 8 hours | 1 day | 2017-04-03 | 2017-04-03
-Contact Us | 2 hours | 1 day | 2017-04-04 | 2017-04-04
-login page | 2 hours
-search page | 2 hours
-about Us and sub pages About Balloony,Location Map + Contacts,Our Staff | 2 hours
-Messages pages | 8 hours | 1 day | 2017-04-05 | 2017-04-05
-send A Gift and other submenu not found without the Regular Latest Balloons and confetti | 8 hours | 1 day | 2017-04-06 | 2017-04-06
-product page and Details | 8 hours | 2 days | 2017-04-09 | 2017-04-10
-Balloons and sub category and sub for sub category template | 8 hours
-party Supplies and sub category and sub for sub category | 8 hours | 1 day | 2017-04-11 | 2017-04-11
-arabic language for Balloons & Party Supplies | 32 hours | 3 days | 2017-04-12 | 2017-04-16
- test for all build in project | 16 hours | 2 days
Customize your Party & Event
-home page |  | 2 days | 2017-04-18 | 2017-04-19
-Main Menu | 4 hours
-Main Banner | 4 hours
-booking events form | 4 hours
-latest Services | 4 hours
-servies page and details | 16 hours | 2 days | 2017-04-23 | 2017-04-24
- booking events all processes | 64 hours | 8 days | 2017-04-25 | 2017-05-04
-arabic language in customize your party & event | 16 hours | 2 days | 07/05/2017 | 2017-05-08
-live chat | 24 hours | 3 days | 2017-05-09 | 2017-05-11
-sms notification | 8 hours | 1 day | 14/05/2017 | 2017-05-14